## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
1FHLwQPyT0ipBb2XuE9Up8kALxSk | Team roles & timeline finalization | Topic finalization & Approval | Completed | Low | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 06/20/2025 | 06/22/2025 | 06/25/2025 | false | false | 06/25/2025 | NAWARATHNA D.N.D.G it22589040 | 2/2 | define time line;Assign team roles | Red
8Ow4jmJKgUmYfCTZ38XZIMkAA3Wi | Identify research gap | Literature Review | Completed | Important | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 07/11/2025 | 07/13/2025 | 07/16/2025 | false | false | 07/16/2025 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Refine research gap;Compare existing solutions | Plum
BOvSONqy6USEcGC91Xvth8kAOvKB | Final topic selection | Topic finalization & Approval | Completed | Urgent | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 06/30/2025 | 07/02/2025 | 07/07/2025 | false | false | 07/07/2025 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Select final topic;Compare shortlisted topic
FG69W6Y9r0iOF4RXeRw-GMkANo80 | Editing & Formatting | Research Paper Presentation | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 01/14/2026 | 01/16/2026 | 01/20/2026 | false | false | 01/20/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Format paper;Review proofread | Gray
Gnowq_RhpUiQQ_KWOfA9ZskACJBa | Risk analysis | Risk Management & Contingency Planning | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 08/03/2025 | 08/05/2025 | 08/09/2025 | false | false | 08/09/2025 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Prioritize risks;Evaluate risk impact
JjFERXb9X0SxqQ8DZljm9MkACu09 | Integrate backend | Prepare Research Website | Completed | Important | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 03/18/2026 | 03/20/2026 | 03/24/2026 | false | false | 03/24/2026 | NAWARATHNA D.N.D.G it22589040 |  |  | Blue
KnOWxAUKQkOdfuZ1FqcBMskAHqMu | Write README and setup guide | Documentation (Report,README) | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 12/26/2025 | 12/28/2025 | 12/31/2025 | false | false | 12/31/2025 | NAWARATHNA D.N.D.G it22589040 | 2/2 | write setup instructions;add usage guide | Orange
SPQBiN5qekaEoubwebu-W8kABvU9 | Review & finalize design | Design/Architecture | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 09/19/2025 | 09/21/2025 | 09/28/2025 | false | false | 09/28/2025 | NAWARATHNA D.N.D.G it22589040 |  |  | Aqua
U2T-vYeQPkeTIXr4la5yU8kAJxFi | plan website structure | Prepare Research Website | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 03/19/2026 | 03/21/2026 | 03/24/2026 | false | false | 03/24/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | create sitemap and navigation flow;define website pages | Teal
VvliLa0XT0GGS1s5CYsaMskAGjwT | Highlight project contribution | Final Presentation | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 04/22/2026 | 04/24/2026 | 05/01/2026 | false | false | 05/01/2026 | NAWARATHNA D.N.D.G it22589040 |  |  | Purple
WDQOJNwhRUi3DvT1ABw38skAHpwx | System evaluation | Testing & Evaluation for PP1 | Completed | Low | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 02/12/2026 | 02/14/2026 | 02/20/2026 | false | false | 02/20/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Evaluate performance;Prepare test results | Aqua
XEiLHlLoD0u9HoZKkm3G-ckAKQ-S | Frontend development | Implementation | In progress | Important | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 12/21/2025 | 12/23/2025 | 12/26/2025 | false | true | 12/26/2025 |  | 1/1 | Built ui component
_rdbrkIEw0mX_qWClKcGnMkAMG2u | Add references and citations | Prepare Final Report | In progress | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 03/15/2026 | 03/17/2026 | 03/20/2026 | false | true | 03/20/2026 |  | 2/2 | insert diagrams, tablets;Add refernces and citations | Dark green
d8pr31F9UUCdRj6wARhHpckABVat | Prepare presentation slides | Progress Presentation 2 | Completed | Urgent | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 01/10/2026 | 01/12/2026 | 01/15/2026 | false | false | 01/15/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | design slides;Add visuals (diagrams,charts,screenshot) | Aqua
iI0mkalgj02z72fKkGOo9ckAB7I3 | Review & Finalization | Prepare Final Report | In progress | Important | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 05/06/2026 | 05/08/2026 | 05/12/2026 | false | false | 05/12/2026 |  | 2/2 | Proofread for grammer and technical accuracy;perform final validation | Lime
mFyzp4vQyk2rntUZt9N1zckACs-I | Prepare presentation | Progress Presentation 1 | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 12/28/2025 | 12/30/2025 | 01/03/2026 | false | false | 01/03/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Create presentation slides;Add visuals & diagrams | Lime
sAvgtavHK0Cy7EeJBkDRJ8kAJNde | finalize report formatting | Documentation (Report,README) | Completed | Medium | NAWARATHNA D.N.D.G it22589040 | NAWARATHNA D.N.D.G it22589040 | 12/26/2025 | 12/28/2025 | 01/04/2026 | false | false | 01/04/2026 | NAWARATHNA D.N.D.G it22589040 | 2/2 | Proofread content;format report | Silver
-AJKrf25P0e770MAy77p-skAGH1R | Rehearsal & final adjusments | Final Presentation | Not started | Important | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 04/26/2026 |  | 05/05/2026 | false | false |  |  | 0/2 | refine slides, demo flow and speaking claruty;practice full presentation with time management | Pink
0hFFGCHfo060NJma1WbKdckAO8iV | Complete all report section | Prepare Final Report | Completed | Urgent | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 03/15/2026 | 03/17/2026 | 03/20/2026 | false | false | 03/20/2026 | WEERASIRI A W S M it22895950 | 2/2 | merge all individual sections;organize chapters | Dark gray
29sHiBxFuEmny2IjZa188MkAEmZe | Data source identification | data Collection & Preparation Planning | Completed | Low | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 10/15/2025 | 10/17/2025 | 10/24/2025 | false | false | 10/24/2025 | WEERASIRI A W S M it22895950 | 1/1 | collect row data | Brown
2zniS4jti0qBEGQGPEOgc8kAM69I | Database design | Design/Architecture | Completed | Important | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 09/18/2025 | 09/20/2025 | 09/24/2025 | false | false | 09/24/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Define schema;Design ER diagram | Plum
3TvCuLGNa0qTAb6DHIaNYckALFRE | Handle error handling and validation | Implementation | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 11/19/2025 | 11/21/2025 | 11/28/2025 | false | false | 11/28/2025 | WEERASIRI A W S M it22895950 |  |  | Bronze
3b-EQ9E-iE-uQRQMNRPFA8kAKbNk | Research existing work | Literature Review | Completed | Important | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 03/13/2025 | 03/15/2025 | 03/21/2025 | false | false | 03/21/2025 | DILRANGI P K T S it22509086 | 2/2 | Collect research paper;analyze key approaches | Brown
4fUVxMbKDEeCGF-gt7paDckACxjK | Feasibility & relevent analysis | Pre-Planning & Topic Selection | Completed | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 06/16/2025 | 06/18/2025 | 06/22/2025 | false | false | 06/22/2025 | DILRANGI P K T S it22509086 | 2/2 | Analyze technical feasibility;Evaluate scope & constrains
5FHEwDCEV0-LeSmfnOCTTMkAKch_ | Risk mitigation planning | Risk Management & Contingency Planning | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 09/04/2025 | 09/06/2025 | 09/12/2025 | false | false | 09/12/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Prepare contingency plan;Define mitigation strategies
5ejRS7kdD06CMKvi6Qvs5skAMkh_ | Individual component selection | Pre-Planning & Topic Selection | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 06/17/2025 | 06/19/2025 | 06/26/2025 | false | false | 06/26/2025 | WEERASIRI A W S M it22895950
5fGADdY0b0yQhEdtTUNp8MkAA0je | Outline & Structure planning | Research Paper Presentation | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 01/17/2026 | 01/19/2026 | 01/24/2026 | false | false | 01/24/2026 | WEERASIRI A W S M it22895950 | 0/2 | create outline;define sections | Dark blue
6P-FGhPvI0uMqc7HX_yLRskAL_Dl | Technical Documentation | Documentation (Report,README) | Completed | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 02/02/2026 | 02/04/2026 | 02/07/2026 | false | false | 02/07/2026 | DILRANGI P K T S it22509086 | 2/2 | Document achitecture;Write system description | Dark blue
8kTGy04gCky0whpskutl-MkACef9 | Reheasal | Progress Presentation 1 | Completed | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 01/09/2026 | 01/11/2026 | 01/15/2026 | false | false | 01/15/2026 | DILRANGI P K T S it22509086 | 2/2 | Practice presentation;improve timing | Orange
93s5BWWGlEu27YH5eKUJtMkAGcNx | Integrate system components | Implementation | Completed | Important | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 11/14/2025 | 11/16/2025 | 11/22/2025 | false | false | 11/22/2025 | DILRANGI P K T S it22509086 | 4/4 | Adaptive learning path generator;stress level predictor;Attendance tred analyser;Academic risk predictor | Red
Agj0ZGw5TUiGEi3eLzXYxMkAHscW | Practise presentation delivery | Progress Presentation 2 | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 01/21/2026 | 01/23/2026 | 01/28/2026 | false | false | 01/28/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Practise presentation with time management;Refine slides and speaking points | Dark gray
BzdD7_-AhUiOShjpqvwbyMkABewT | Update project progress | Progress Presentation 2 | Completed | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 01/15/2026 | 01/17/2026 | 01/22/2026 | false | false | 01/22/2026 | DILRANGI P K T S it22509086 | 2/2 | Select key feature to demostrate;test demo flow and avoid errors | Purple
CQTghKz6ekW0ruSLYKkeJ8kAK4pA | Integrating testing | Testing & Evaluation for PP1 | Completed | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 02/11/2026 | 02/13/2026 | 02/17/2026 | false | false | 02/17/2026 | DILRANGI P K T S it22509086 | 2/2 | Resolve integration issues;Test module integrations | Lime
Ex570c-1SE6jZjrqBa9N9skAEMVu | Develop core module | Implementation | Completed | Low | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 10/24/2025 | 10/26/2025 | 10/30/2025 | false | false | 10/30/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | implement core logic and model;optimize performance | Yellow
FNSouWYRh022Jexr-HQVSskAL_gY | Add project content | Prepare Research Website | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 03/20/2026 | 03/22/2026 | 03/27/2026 | false | false | 03/27/2026 | WEERASIRI A W S M it22895950 |  |  | Purple
GTk73yaieEqs6qM5Bp6M1ckAKhAx | Final review before submission | Progress Presentation 2 | In progress | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 01/17/2026 | 01/19/2026 | 01/22/2026 | false | true | 01/22/2026 |  |  |  | Light blue
Go-TnkkqlUmsgPGqDZWtK8kAEWtQ | UI/UX Design | Design/Architecture | Completed | Low | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 09/17/2025 | 09/19/2025 | 09/22/2025 | false | false | 09/22/2025 | DILRANGI P K T S it22509086 | 2/2 | Create wireframes;Design final UI | Light gray
Hiu4HZHg5ECVUKTv_2kwHskADyw0 | Prepare demo | Final Presentation | Not started | Important | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 03/28/2026 |  | 04/05/2026 | false | true |  |  | 0/2 | select key features to showcase;test demo flow and ensure system stability | Light blue
ICjF62ai-U-xyUWmPVSJaskAAfnZ | Select target conference | Research Paper Publication | In progress | Important | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 02/08/2026 | 02/10/2026 | 02/13/2026 | false | true | 02/13/2026 |  | 0/2 | Check submission guideline;Review conference scope | Yellow
IDcrBAsJwkW4gTwWlcoQuckAKtHH | Define non-functional requirements | Requirement Analysis | Completed | Important | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 08/13/2025 | 08/15/2025 | 08/20/2025 | false | false | 08/20/2025 | DILRANGI P K T S it22509086 | 2/2 | Define security constrains;Define performance criteria
LFEObhkn_U6gL_Ei2-TSTskAP-DU | Risk identification | Risk Management & Contingency Planning | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 09/02/2025 | 09/04/2025 | 09/09/2025 | false | false | 09/09/2025 | WEERASIRI A W S M it22895950 | 2/2 | List possible risks;Categorize risks
MGbJVq3udEC-LOz5y_LDIckAL0jh | Backend development | Implementation | Completed | Urgent | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 10/14/2025 | 10/16/2025 | 10/23/2025 | false | false | 10/23/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Develop APIs;Connect database | Bronze
PSx83pliL0yxD3ohWnnWP8kADzZZ | Checked the individual component and fix the bugs | Testing & Evaluation for PP1 | In progress | Important | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 12/24/2025 | 12/26/2025 | 12/31/2025 | false | true | 12/31/2025 |  | 4/4 | Acadamic Risk predictor;Stress level predictor;Adaptive learning path generator;Attendance trend analyzer | Red
QfqBhe7VyUOF5sFNrAdtlskAJg_8 | Check the repository | Testing & Evaluation for PP1 | Completed | Low | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 12/13/2025 | 12/15/2025 | 12/18/2025 | false | false | 12/18/2025 | RANASINGHA.R.A.C.A it22577542 |  |  | Purple
Uyq9-E6l40mW_b-GLRt8gckACudt | UI/UX design | Prepare Research Website | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 03/18/2026 | 03/20/2026 | 03/26/2026 | false | false | 03/26/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Design wireframe;Apply final UI design | Teal
V6yXi90WEkGPRqrxzbDa2ckAMSju | Prepare literature review section draft | Literature Review | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 07/21/2025 | 07/23/2025 | 07/30/2025 | false | false | 07/30/2025 | WEERASIRI A W S M it22895950 |  |  | Lavender
V8vQkiYKxUifufDlU7VpNskAMgGi | Fix the bugs | Testing & Evaluation for PP1 | Completed | Urgent | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 12/25/2025 | 12/27/2025 | 12/30/2025 | false | false | 12/30/2025 | RANASINGHA.R.A.C.A it22577542 | 1/1 | Fix errors | Peach
ZXyWbL7ZCUCdVHYlbPzNTMkAEAc1 | Topic justification draft | Pre-Planning & Topic Selection | Completed | Urgent | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 06/22/2025 | 06/24/2025 | 06/30/2025 | false | false | 06/30/2025 | DILRANGI P K T S it22509086
d20i16M0vka-xo-pHQLnsskAHVa7 | Data preprocessing & labelling | data Collection & Preparation Planning | Completed | Low | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 10/18/2025 | 10/20/2025 | 10/23/2025 | false | false | 10/23/2025 | DILRANGI P K T S it22509086 | 2/2 | remove noice & duplication;handle missing values | Purple
l_q3vVoGi0W6i7-QdPD1bskAOqAK | Testing & Development | Prepare Research Website | Completed | Urgent | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 12/26/2025 | 12/28/2025 | 01/04/2026 | false | false | 01/04/2026 | DILRANGI P K T S it22509086 | 2/2 | deploy website;test responziveness
mTYh9cwQMUGn3EJ3SdZ9DckAKiYe | Document requirement specification | Requirement Analysis | Completed | Low | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 08/14/2025 | 08/16/2025 | 08/21/2025 | false | false | 08/21/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Review and finalize;Prepare SRS Document
n-xvfPIXzECbLmheXjm7UskALNaa | Write final discussions and conclution | Prepare Final Report | In progress | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 02/23/2026 | 02/25/2026 | 03/04/2026 | false | true | 03/04/2026 |  | 1/2 | compleate discussion and analysis sections;Write conclusion and future work | Yellow
nAXl2vFMuUyawL8aty9E_8kABI3f | Assign component ownership and reviews | Topic finalization & Approval | Not started | Medium |  | NAWARATHNA D.N.D.G it22589040 | 04/30/2026 |  |  | false | false
oujZX76E3kOr8FFZOkvceMkAPm7Z | Write paper | Research Paper Presentation | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 01/28/2026 | 01/30/2026 | 02/04/2026 | false | false | 02/04/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Write methodology;Write results & Discussion | Teal
p0_DTreXfUCuvSZnccCP_ckALJMy | Prepare submission materials | Research Paper Publication | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 02/02/2026 | 02/04/2026 | 02/11/2026 | false | false | 02/11/2026 | RANASINGHA.R.A.C.A it22577542 |  |  | Lime
pBjR5mo8HUq0ThCeVVy1iskAJ0zH | Supervisor approval & kickoff | Topic finalization & Approval | Completed | Urgent | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 07/14/2025 | 07/16/2025 | 07/20/2025 | false | false | 07/20/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Prepare proposal summary;get supervisor approval | Lime
pGeWusTUVE6CkdcR7Z8vm8kAI2bX | Summarize technical implementation | Progress Presentation 2 | Completed | Medium | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 01/26/2026 | 01/28/2026 | 01/31/2026 | false | false | 01/31/2026 | WEERASIRI A W S M it22895950 | 0/2 | summarize completed work;Highlight improvements | Brown
pMyrIvBRUEm2OHOee2m538kAM7St | Select tool & technologies | Design/Architecture | Completed | Low | WEERASIRI A W S M it22895950 | NAWARATHNA D.N.D.G it22589040 | 09/19/2025 | 09/21/2025 | 09/24/2025 | false | false | 09/24/2025 | WEERASIRI A W S M it22895950 |  |  | Blue
tH4O2cjMGUGAj3AIowfg5ckANO0q | Final review & submission presentation | Research Paper Presentation | In progress | Medium | DILRANGI P K T S it22509086 | NAWARATHNA D.N.D.G it22589040 | 02/03/2026 | 02/05/2026 | 02/09/2026 | false | true | 02/09/2026 |  | 2/2 | Performe plagiarism check & corrections;Prepare submission files | Yellow
uo2L2ZAtxEmu0oTC7kfuTskADdrV | Data collection strategy | data Collection & Preparation Planning | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 10/09/2025 | 10/11/2025 | 10/16/2025 | false | false | 10/16/2025 | RANASINGHA.R.A.C.A it22577542 | 1/1 | Transform dataset | Yellow
vALcFdZ_hUagzA7rJ6TBc8kAAEGA | Prepare system demo | Progress Presentation 1 | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 01/02/2026 | 01/04/2026 | 01/07/2026 | false | false | 01/07/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Test demo flow;Prepare system demo | Marigold
waC-EjaK0UKiFeiuKCO42ckAO83r | Formatting & Standardization | Prepare Final Report | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 03/21/2026 | 03/23/2026 | 03/27/2026 | false | false | 03/27/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | apply formatting guidelines;Ensure consistency (numbering, captions, alignment) | Light blue
wjfTXTLyhkCIDRDLxQlX4skAKMXT | Create system architecture diagram | Design/Architecture | Completed | Important | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 09/20/2025 | 09/22/2025 | 09/25/2025 | false | false | 09/25/2025 | RANASINGHA.R.A.C.A it22577542 |  |  | Green
xFZsgw7ad0uT1qIvCnlqsckALC-S | Define functional requirement | Requirement Analysis | Completed | Medium | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 08/16/2025 | 08/18/2025 | 08/24/2025 | false | false | 08/24/2025 | RANASINGHA.R.A.C.A it22577542 | 2/2 | Identify user needs;Define system functions | Teal
yR0zH9l7q02Rk9AnXeXGw8kAM85t | create final presentation slides | Final Presentation | Completed | Important | RANASINGHA.R.A.C.A it22577542 | NAWARATHNA D.N.D.G it22589040 | 04/24/2026 | 04/26/2026 | 05/01/2026 | false | false | 05/01/2026 | RANASINGHA.R.A.C.A it22577542 | 2/2 | apply consistent design;create slide with visuals

## Plan name
Plan name | ENHANCING TOURISM DIGITAL TWINS WITH REAL-TIME, BILATERAL DATA ACROSS DIVERSE DOMAINS
Plan ID | 58ro5A-WhUGicDhajzZVUskAGa6h
Date of export | 05/01/2026